KPMG - NYC Hub Walls

Prepared by: Bridgewater Studio

Client: KPMG, with coordination through Spark Chicago

Project: NYC Hub Walls

Date: 10/20/2025

Lead time: four to six weeks from approvals, artwork release, and site access

Executive summary

We will fabricate and deliver the steel hub wall panels for Levels 19, 20, and 21 using a sandblast process with matte clear powdercoat. The plan prioritizes finish quality, predictable sequencing, and a calm install with Bridgewater supervision alongside GC labor.

Preliminary workback schedule

| Date | Milestone |
| --- | --- |
| 10/22/2025 | Approvals and artwork release |
| 10/25/2025 | Site verification and 3D scan |
| 10/28/2025 | Panel raw materials ordered |
| 11/05/2025 | Panel selection by location and visual layout per wall, artwork and mask plotting complete |
| 11/27/2025–11/28/2025 | Thanksgiving holiday, no production or deliveries |
| 12/03/2025 | Blasting, powdercoat, lamination, and protection complete |
| 12/09/2025 | Deliver to site and begin installation window (post Thanksgiving) |
| 12/19/2025 | Installation complete |

Budget

| Zone | Item | Brief Description | Budget |
| --- | --- | --- | --- |
| Level 19 - West Elevator Lobby | Steel hub wall assembly fabrication and finish | Fabricate two hot rolled steel panels per shop elevations with sandblast etched linework, laminated to 3/4 in plywood with Z clips. Includes surface prep, rust inhibitor, and matte clear powdercoat. Shops include seam map and mask registration for continuous artwork. | $8,015.00 |
| Level 19 - South Hub Wall | Steel hub wall assembly fabrication and finish | Fabricate six hot rolled steel panels with engineered sandblast mask and uniform blast passes. Laminate to 3/4 in plywood with Z clips and provide protection film through install. Includes matte clear powdercoat and QC per approved mockup. | $22,280.00 |
| Level 20 - West Elevator Lobby | Steel hub wall assembly fabrication and finish | Fabricate two steel panels per brand elevation with equalized seams for clean rhythm. Includes mask plotting, blast, lamination to plywood, and matte clear powdercoat. Deliver with retain sample and handling edge guards. | $8,230.00 |
| Level 20 - South Hub Wall | Steel hub wall assembly fabrication and finish | Fabricate six steel panels with consistent sandblast depth and crisp edges. Provide Z clip layout, device templates, and final matte clear powdercoat. Artwork alignment verified across seams before finish. | $22,745.00 |
| Level 21 - West Elevator Lobby | Steel hub wall assembly fabrication and finish | Fabricate two steel panels matched to field datum and adjacent trims. Includes mask application, blast cycles, lamination, and matte clear powdercoat. Coordinate left side trim condition to maintain jamb alignment. | $7,995.00 |
| Level 21 - South Hub Wall | Steel hub wall assembly fabrication and finish | Fabricate six steel panels with seam rhythm tuned to the artwork spans. Includes lamination to plywood, Z clips, and matte clear powdercoat. Provide first article for visual standard before full run. | $22,985.00 |
| Project Support | Site verification and 3D scan | Travel to site to measure, verify datums, and scan wall fields for exact panelization. Supports cutout templates and reduces rework risk. | $3,595.00 |
| Project Support | Artwork and mask plotting | Prepare sandblast artwork for each panel, generate engineered masks, and perform registration checks across seams before production. | $19,440.00 |
| Project Support | Blasting vendor coordination and transport cycles | Coordinate outsourced blast cabinet runs for oversized panels, manage pickup and return inspections prior to powder. | $4,760.00 |
| Project Support | Installation labor | Includes travel and per diem, on site coordination, daily briefings, and close out. Supervisors lead install with GC labor to optimize cost without sacrificing quality. | $21,735.00 |
| Project Support | Installation equipment rental | Site lifts, scaffolds, carts, small tools, and rigging hardware suited to access constraints. Includes delivery, pickup, and consumables. | $3,885.00 |
| Project Support | Shipping and Freight | Crating, LTL or FTL, and scheduled deliveries. Placeholder to be adjusted. | $8,500.00 |
| Project Support | Professional Services and Project Management | Project management and related activities including schedule and stakeholder coordination, submittals and RFIs, vendor integration, quality control, risk and change tracking, documentation, and design to fabrication handoffs with standing status meetings. | $16,750.00 |
|  |  | TOTAL ESTIMATED BUDGET | $170,915.00 |

Assumptions and clarifications

Bridgewater supervision, GC labor for install.

Device cutouts verified by rigid templates after site scan.

Top trim by Drive21. Side and base trims by STI.

Excludes permits, after hours fees, union jurisdiction costs, or building specific premiums unless noted.

Any on site mockup to be confirmed.

## Next steps

Approve the workback schedule and budget.

Release final artwork files for mask plotting.

Confirm site access, dock and elevator details, and install window.

We will lock vendor windows for blasting and powder and proceed on the dates above.

Sincerely,

Eric Cup

President